# Video 1:

Importance of Project Schedules

- often cite delivering projects on time as biggest challenge

- Schedule issues are the main reason for conflicts on projects

- Time has the least amount of flexibility

Project schedule management processes

- Planning schedule management

The project team uses expert judgement, analytical techniques & meetings to develop the schedule management plan

Schedule management plan:

    - Project schedule model development

    - Scheduling methodology

    - Level of accuracy & units of measure

    - Control thresholds

    - Rules of performance measurement

    - Reporting formats

    - Process descriptions

- Defining activities-further defining scope

- Develop a more detailed WBS and supporting explanations to understand all the work to be done

- Activity/task: an element of work normally found on the WBS (work breakdown structure) that has an expected duration, a cost and resource requirements

- Goal: To ensure project team completely understand all the work

Outputs:

    - activity list: a tabulation of activities to be included on a project schedule

      - Activity name

      - Activity identifier/number

      - Brief description of activity

      - Activity attributes provide more information

    - activity attributes

      - Predecessors

      - Successors

      - Logical relationships

      - Leads & lags

      - Resource requirements

      - Constraints

      - Imposed dates

      - Assumptions related to activity

    - a milestone lists

- a significant event that normally has no duration

- often takes several activities & a lots of work to complete a milestone

- useful tools for setting schedule goals & monitoring progress

- e.g., obtaining customer sign-off on key documents

- completion of specific products

    - project management plan updates

Sequencing activities-further defining time

  - reviewing activities and determining dependencies

  - dependency or relationship is the sequencing of project activities or tasks

  - Relationships or dependencies among activities has a significant impact on project schedule

  - Identifying & documenting the relationships between project activities

- Estimating activity durations-further defining time and cost

- Developing the schedule

Analysing activity sequences, activity resource estimates & activity duration estimates

To determine the start & end date of the project

Tools & techniques:

Gantt charts

Critical path analysis

Critical chain scheduling

PERT analysis

- Controlling the schedule

# Video 2

Sequencing Activities

- reviewing activities determining dependencies

- dependency or relationship is the sequencing of project activities or tasks

- Relationships or dependencies among activities has a significant impact on project schedule

Three types of Dependencies

- Mandatory dependencies - (hard logic) inherent in the nature of the work being performed on a project

- Discretionary dependencies – (soft logic) should be used with care since they may limit later scheduling options

- External dependencies- involve relationships between project and non-project activities

Network Diagrams

- Network diagrams for showing activity sequencing is a schematic display of the logical relationships among, or sequencing of, project activities

- Two main formats

  - ADM Arrow diagramming (Activity-on-Arrow AOA)

    - Activities are represented by arrows

    - Nodes are the starting and ending

    - Can only show finish-to-start dependencies

    - Process

      - Find all of the activities

      - working from left to right.

      - no arrows should cross

  - PDM Precedence diagramming (Activity-on-Node)

    - Activities are represented by boxes

    - Arrows show relationships

    - Better at showing different types of dependencies

  - Task Dependency

# Video 3

Estimating Activity Resources

- Before estimating activity durations, must have good idea of the quantity and type of resources that will be assigned to each activity

- resources are people, equipment, and materials

- resource breakdown structure is a hierarchical structure that identifies the project’s resources by category and type

Activity Duration Estimating

- Duration includes actual amount of time worked on an activity plus elapsed time

- Effort is the number of workdays or work hours and does not normally equal duration

- People doing the work should help create estimates

- Three-Point Estimates

Program Evaluation and Review Technique PERT

- network analysis technique to estimate project duration when there is a high degree of uncertainty about the individual activity duration estimates

- PERT uses probabilistic time estimates

  - applies the critical path method (CPM) to a weighted duration estimate

  - duration estimates based on three-point estimate

Developing the Schedule

- Ultimate goal is to create a realistic project schedule provides a basis for monitoring project progress

- tools and techniques:

  - Gantt charts,

    - displaying project schedule

    - Adding Milestones- emphasize important events or accomplishments

    - Milestones: Specific, Measurable, Assignable, Realistic, Time-framed

  - critical path analysis

    - network diagramming technique to predict total project duration

    - critical path is the series of activities determines the earliest time

    - longest path

    - Slack or float is the amount of time an activity may be delayed

Free slack or free float: the early start of any immediately following activities

Total slack or total float: the planned project finish date

forward pass: determines the early start and finish dates

backward pass: the late start and finish dates

    - Critical Path to Shorten a Project Schedule

    - Three main techniques

      - Shortening durations of critical activities- adding more resources or changing their scope

      - Crashing activities- greatest amount of schedule compression for the least incremental cost

      - Fast tracking activities- parallel or overlapping

  - critical chain scheduling

    - method of scheduling considers limited resources and includes buffers to protect the project completion date

    - Uses the Theory of Constraints (TOC)

      - improving other things besides the constraint does nothing to improve the system

      - important concept is the availability of scarce resources

    - Attempts to minimize multitasking when a resource works on more than one task at a time

- Buffers and Critical Chain

    - buffer is additional time; people often add a buffer to each task and use it if it’s needed or not

    - Critical chain scheduling removes buffers

      - project buffer or additional time added before the project’s due date

      - feeding buffers or additional time added before tasks on the critical path

  - PERT (Program Evaluation and Review Technique) analysis

# Video 4

Controlling the Schedule

- Goals are to know the status of the schedule, influence factors cause schedule changes, determine that the schedule has changed, and manage changes

- Tools and techniques: Progress reports, schedule change control system, Project management software, Variance analysis, Performance management, Resource optimization techniques

Agile and Time Management

- Core values Agile Software Development are:

  - Customer collaboration over contract negotiation

  - Responding to change over following a plan

- product owner defines and prioritizes the work to be done within a spring, so collaboration and time management are designed into the process

- Teams focus on producing a useful product

- Don’t emphasize defining all the work before scheduling it

Schedule Control Suggestions

- Perform reality checks on schedules

- Allow for accident

- Don’t plan for everyone to work at 100% capacity all the time

- Hold progress meetings with stakeholders and be clear and honest in communicating schedule issue

Reality Checks on Scheduling

- review the draft schedule or estimated completion date

- Prepare a more detailed schedule

- Make sure the schedule is realistic and followed

- High-level periodic reviews

- Alert top management well if there are schedule problems

Working with People Issues

- Strong leadership helps projects succeed more than good PERT charts

- Project managers should

  - Empowerment

  - Incentives

  - Discipline

  - negotiation

Using Software to Assist

- Software for facilitating communications helps people exchange schedule-related information

- Decision support models help analyze trade-offs that can be made

- Project management software can help in various time management areas

Video 2:

Sequencing activities:

Review activities and determine dependencies

Dependency/relationship: the sequencing of project activities/tasks

3 types of dependencies:

- Mandatory:

inherit in the nature of the work being performed on a project

sometimes referred to as hard logic

- Discretionary:

Defined by project team

Sometimes referred to as soft logic

May limit later scheduling options

- External:

Relationships between project & non-project activities

Networking diagrams:

Preferred technique for showing activity sequencing

Schematic display of the logical relationships among or sequencing of project activities

Main formats:

- Arrow diagramming method (ADM)

Also called Activity-on-Arrow (AOA)

Nodes/circles: starting & ending points of activities

Can only show finish-to-start dependencies

Burst: a single node followed by 2+ activities

Merge: 2+ nodes precede a single node

- Precedence diagramming method (PDM)

Also called Activity-on-Node (AON)

Activities represented by boxes

Arrows show relationships between activities

More popular

Used by project management software

Better at showing different types of dependencies

Task dependency:

- Finish-to-start (FS)

- Start-to-start (SS)

- Finish-to-finish (FF)

- Start-to-finish (SF)

Video 3:

Resources: people, equipment & materials

Resource breakdown structure: a hierarchical structure that identifies the project’s resources by category and type

Duration:

Actual amount of time worked on an activity + elapsed time

Effort:

The number of workdays or work hours required to complete a task

Three-point estimates:

- Optimistic

- Most likely

- Pessimistic

Program evaluation and review technique (PERT):

A network analysis technique used to estimate project duration when there is a high degree of uncertainty about the individual activity duration estimates

Use probabilistic time estimates:

- Apply critical path method (CPM) to a weighted average duration estimate

- Duration based on three-point estimate

Weighted average= (optimistic + 4*most likely + pessimistic)/6

Gantt chart:

Provide a standard format for displaying project schedule information by listing project activities & corresponding start and finish dates in a calendar format

SMART criteria for milestones:

- Specific

- Measurable

- Assignable

- Realistic

- Time-framed

Supplementary video:

CPM (critical path method):

A network diagramming technique used to predict total project duration

Critical path:

the series of activities that determine the earliest time by which the project can be completed

longest path through the network diagram

least amount free slack/float (the amount of time an activity may be delayed without delaying a succeeding activity/project finish date)

total slack/float:

the amount of time an activity may be delayed from its early start without delaying the planned project finish date