# Video 1:

Importance of Project Cost Management

- IT projects have a poor track record

- A perceived reason for cost overruns is involve new technology or business processes pose an inherent risk

- using good project cost management can change this

Cost overrun: the additional percentage or dollar amount by which actual costs exceed estimates

Cost: a resource sacrificed/ foregone to achieve a specific objective or sth given up in exchange

Project cost management: the processes required to ensure that the project is completed within an approved budget

- Planning cost management: determine policies, procedures, documentation that will be used for planning, executing and controlling project cost

- Estimating costs: develop an approximation or estimate of the costs of the resources needed to complete a project

- Determining the budget: allocate overall cost estimate to individual work items to establish a baseline for measuring performance

- Controlling cost: control changes to the project budget

Profits: revenues – expenditures

Profit margin: revenues/profits

Life cycle costing: consider total cost of ownership (development + support)

Cash flow analysis: estimated annual costs & benefits for a project

Types of costs & benefits:

- Tangible costs/benefits: can easily measure in dollars

- Intangible costs/benefits: difficult to measure in monetary terms

- Direct costs: directly related to producing the products & services

- Indirect costs: not directly related to producing the products & services

- Sunk cost: money that has been spent in the past

Basic principles:

- Learning curve theory:

When many items are produced repetitively, the unit cost of those items decreases in a regular pattern as more units are produced

- Reserves:

Dollars included in a cost estimate to mitigate cost risk by allowing for future situations that are difficult to predict

    - Contingency reserves:

known unkowns (future situations that may be partially planned for)

included in the project cost baseline

    - Management reserves:

Unkown unkowns (future situations that are unpredictable

Video 2:

Cost management plan:

- Level of accuracy & units of measure

- Organisational procedure links

- Control thresholds

- Rules of performance measurement

- Reporting formats

- Process descriptions

Estimating Costs

- Project managers must take cost estimates seriously

- Estimates done at various stages of a project and should become more accurate as time

- Most project costs are labour costs

- Types of Cost Estimates

Cost estimation tools & techniques:

- Analogous/top-down: use actual cost of pervious, similar project as the basis

- Bottom-up: estimate individual work items/activities and sum up

- Parametric modelling: use project characteristics/parameters in a mathematical model

Problems with IT Cost Estimates

- Estimates are done too quickly

- lack experience

- biased toward underestimation

- Management desires accuracy

# Video 2

Determining the Budget

- Cost budgeting allocating the project cost estimate to individual work items over time

- WBS is a required input to the cost budgeting process since it defines the work items

- Important goal cost baseline:

  - project managers use to measure and monitor cost performance

  - members should document any assumptions made when developing the cost baseline

Controlling Costs

- cost control includes

  - Monitoring cost performance

  - Ensuring that only appropriate project changes are included in a revised cost baseline

  - stakeholders of authorised changes to the project that will affect costs

- Change control system to define procedures for changing the cost baseline is necessary

- Tools

  - Performance review meetings

  - Performance measurement

  - Earned value management

    - integrates scope, time, and cost data

    - Given a baseline determine how well the project is meeting its goals

    - must enter actual information

      - whether or not a WBS item was completed

      - how much of the work was completed

      - how much completed work cost

    - planned value (PV) called the budget, is that portion of the approved total cost estimate planned to be spent

    - Actual cost (AC) total of direct and indirect costs incurred in accomplishing work

    - earned value (EV) is an estimate of the value of the physical work actually completed

    - EV is based on the original planned costs the rate at which the team is completing work

- Rate of Performance

  - actual work completed to the percentage of work planned to have been completed at any given time

pv is planned value

Rules:

- Negative numbers for cost and schedule variance indicate problems

- CPI and SPI less than 100% indicate problems

  - the project is costing more than planned or taking longer than planned

- CPI can be used to calculate the estimate at completion estimate of what it will cost to complete the project based on performance to date.

- budget at completion BAC original total budget for the project

Project Portfolio Management

- collect and control an entire suite of projects or investments in a portfolio

- Five levels

  - Put all your projects in one database

  - Prioritize the projects in your database

  - Divide your projects into two or three budgets based on type of investment

  - Automate the repository

- Benefits

  - Reduced redundant projects and coordinated those with overlap

  - it makes sense to view them as portfolios and track their progress as a whole

  - help reduce costs

# Video 4:

traditional and Agile Cost Management

Managing Cost in Agile

- cost is a direct expression of project time

- Quite easy to determine team cost scum team have a set team cost that be the same for each sprint

- Once we estimate the development speed, determine how many sprints the project will take and know how much the scrum team will cost

Ways to lower project costs

- Self-funding project

- Lowering cost by increasing velocity

- Lowering cost by reducing time