## Risk Register
Risk Register for Project Name
Prepared by: |  | SEE SAW |  |  | Date: | 2018-05-09
No. | Rank | Risk | Description | Category | Triggers | Root Cause | Potential Responses | Risk Owner | Probability | Impact | Status | Score | Legend | Numerical Scale:
R01 | 7 | Insufficient web developing skills | Limited developing skills in project team, still some required functionalities of the website hard to acquire. | Technology Risk | The website cannot be developed on time/some functionalities of the website are not met | The project team is lack of website developing skills | Hiring skilled programmer to ensure website is carefully executed | Project manager | Low | Very high | Open | 27 | Very low | 1
R02 | 2 | Over budget | Cost estimate errors results in project running over budget. Deployment on time cannot be met as requested by sponsor. | Financial Risk | The project is running over budget at any stage | Insufficient cost estimation methods at the beginning of the project | New cost estimation | Project manager | Medium | Very high | Open | 45 | low | 3
R03 | 2 | Lack of stakeholders’ involvement | A lack of stakeholder engagement, the project will not be able to finish on time and may fall short of the required project scope. | People | Stakeholder postponed meetings | Stakeholders too busy or fail to see the need for the project. | Clear communications plan | Project manager | Medium | Very high | Open | 45 | medium | 5
R04 | 1 | Resistance to change by employee | Rapid technological change can mean that management and staff at a bank are not able to fully understand the nature of new technology employed by the bank, or technological upgrades provided by service providers. | People | Poor implementation of newer technology. | Inability to provide ongoing support. Deficiencies in system or data integrity or reliability. | Design management and staff training at the planning stage. | Project manager | High | Very high | Open | 63 | high | 7
R05 | 8 | Illegal access to customer data. | Poor security/awareness of customer privacy. | Technology - security | Personal data misused/leaked. | Lack of security in new system | Mitigation – Secured data server, system server, firewall, etc. | Project manager | Medium | Medium | Open | 25 | Very high | 9
R06 | 4 | Forged Cheques | Fake/fraudulent cheques produced by irresponsible party and bank approve the transactions. | People | Forged cheques used to claim money from bank. | Fraud | Avoidance – Verification before finalising the transactions. Secured data server, system server, etc. | Bank | Medium | High | Open | 35
R07 | 4 | Incompatibility | Current website is outdated and is not compatible with the new application | Technology risk | Website goes down when openning the application | Further development was not considered when creating the website | Replacing the old website/ major updates | Bank/ IT support | Medium | High | Open | 35
R08 | 9 | Popularity | The new application attracts demand from old and new customers | Marketing- Technology | The performance is slow during peak hours | The demand for using the application is higher than expectation | Accurate and clear anlysis of the market and demand | Marketing/ Project manager | Low | Medium | Open | 15
R09 | 9 | O&M Cost | Actual operating costs higher than anticipated | Financial Risk | Complicated installation or usage of the new scanner and application | More users requiring support via internet or phone | Setting up online AI robots to auto respond prior to passing to operators | Project Manager/IT support | Low | Medium | Open | 15
R10 | 4 | Information loss | Loss of essential information due to IT failure | Technology risk | Customer could not view uploaded cheques | Lack of maintenance | System tests and auditing data protection systems | Project Manager/IT support | Medium | High | Open | 35
Note on H4: Use TAMA for negative risks -Anthony Wong

## Probability_Impact Matrix
Probability | High |  |  | R04
| Medium |  | R05 | R02 R03 R06 R07 R10
| Low |  | R08 R09 | R01
|  | Low | Medium | High
Impact