# Video 1:

Project scope management:

Define & control what is or what is not included in a project

develop two important outputs

- scope management plan: subsidiary part of the project management plan

  - scope statement-describes the characteristic of the product

    - Project justification

    - description of the project’s deliverable

    - Summary of all project deliverables

    - what determines project success

  - Contents-How

    - prepare a detailed project scope statement

    - create a WBS

    - maintain and approve the WBS

    - control requests for changes

    - obtain formal acceptance of the completed project deliverable

- requirements management plan

  - need to be elicited, analyzed, and recorded in enough detail

  - included in the scope baseline and be measured once project execution begins

  - Methods for Collecting:

    - Interviewing

    - group creativity and decision-making techniques

    - Questionnaires

    - Observation

    - Prototyping

  - Documentation

    - Functional and non-functional requirements

      - non-functional - how the system works,

      - functional - what the system should do

    - Business rules

    - Impacts on any other systems

    - training requirements

    - acceptance criteria

    - Quality requirements

  - requirements traceability matrix (RTM)

Scope:

All work involved in creating the products of the project and the processes used to create them

Deliverable:

A product produced as part of a project (eg. hardware/ software, planning documents, meeting minutes)

Project scope management processes

Planning:

- Planning scope:

Determine how the project’s scope & requirements will be managed

- Collecting requirements:

Define & document the features and functions of the products produced during the project as well as the processes used for creating them

- Defining scope:

Review the project charter, requirements documents & organisational process assets to create a scope statement

- Creating the WBS:

Subdivide the major project deliverables into smaller, more manageable components

Monitoring & controlling:

- Validating scope:

Form acceptance of the project deliverables

- Controlling scope:

Control changes to project scope throughout the life of the project

# Video 2:

Defining Scope:

Project scope statements include

- product scope description

- product user acceptance criteria

- detailed information on all project deliverables

Creating the Work Breakdown Structure (WBS):

- WBS is a deliverable-oriented grouping of the work involved in a project that defines the total scope of the project

- WBS provides the basis for planning and managing project schedules, costs, resources, and changes

- Decomposition- subdividing project deliverables into smaller pieces

- work package is a task at the lowest level of the WBS

- scope baseline includes the project scope statement and WBS and WBS dictionary

Approaches to Developing WBSs

- analogy approach

  - similar projects and tailor to your project

- top-down approach

  - Start with the largest items break them down

- bottom-up approach

  - Mind mapping-radiating out from a core idea to structure ideas

Dictionary and Scope Baseline

- must be explained more so people know what to do

- can estimate how long it will take

- what it will cost to do the work

- WBS dictionary describes detailed information about each WBS item

# Video 3

Validating Scope

- Scope validation formal acceptance of the completed project deliverables

- Acceptance is often achieved customer inspection and then sign-off on key deliverables

Controlling Scope

- Goals of scope control

  - influence the factors that cause scope changes

  - assure changes are processed according to procedures developed as part of integrated change control

  - manage changes when they occur

- Variance is the difference between planned and actual performance

# Video 4

Scope Creep: changes scope baseline of a project (i.e., addition features after scope determined)

The Agile Lifecycle

Envision

- Determine requirements

- Confirm team

- Set up team collaboration

- project charter –describing scope and overall objectives

- Product Data Sheet (PDS)

  - Project description

  - Project objectives

  - Timelines

  - Cost estimates

  - Constraints

  - Prioritisation

Speculate

- Feature based delivery plan

- Estimates for each feature

- requirements for the Sprint

- features to be developed

- Effort estimates for each feature

- Risks will be identified

scope throughout the project

Flipping the Triangle (DSDM Consortium)

different between traditional and Agile Scope Management