## Sheet1
process | knowledge area | process | output
initiating | integration | develop project charter | project charter
| stakeholder | identify stakeholders | stakeholder register
planning | integration | develop project management plan | project management plan
| scope | plan scope management | scope management plan
requirements management plan
|  | collect requirements | requirements documentation
requirements traceability matrix
|  | define scope | project scope statement
project documents updates
|  | create WBS | scope baseline
project documents updates
| schedule | plan schedule management | schedule management plan
|  | define activities | activity list
activity attributes
milestone list
project management plan updates
|  | sequence activities | project schedule network diagrams
project documents updates
|  | estimate activity durations | activity duration estimates
project documents updates
|  | develop schedule | schedule baseline
project schedule
schedule data
project calendars
project management plan updates
project documents updates
| cost | plan cost management | cost management plan
|  | estimate costs | activity cost estimates
basis of estimates
project documents updates
|  | determine budget | cost baseline
project funding requirements
project documents updates
| risk | plan risk management | risk management plan
|  | identify risks | risk register
|  | perform qualitative risk analysis | project documents updates
|  | perform quantitative risk analysis | project documents updates
|  | plan risk responses | project management plan updates
project documents updates
| quality | plan quality management | quality management plan
process improvement plan
quality metrics
quality checklists
project documents updates
| procurement | plan procurement management | procurement management plan
procurment statement of work
procurement documents
source selection criteria
make-or-buy decisions
change requests
procurement documents updates
| communications | plan communications management | communications management plan
project documents updates
| stakeholder | plan stakeholder management | stakeholder management plan
project documents updates
| resource | plan human resource management | human resource plan
excuting | integration | direct and manage project work | `
work performance data
change requests
project management plan updates
project documents updates
| quality | perform quality assurance | change requests
project management plan updates
project documents updates
organisational process assets updates
| procurement | conduct procurements | selected sellers
agreements
resource calendars
change requests
project management plan updates
procurement documents updates
| communications | manage communciations | project communications
project documents updates
project management plan updates
organisational process assets updates
| stakeholder | manage stakeholder engagement | issue log
change requests
project management plan updates
project documents updates
organisational process assets updates
| resource | acquire project team | project staff assignments
resource calendars
project management plan updates
|  | develop project team | team performance assessments
enterprise environmental factors updates
|  | manage project team | change requests
project management plan updates
procurement documents updates
enterprise environmental factors updates
organisational process assets updates
monitoring & controlling | integration | monitor and control project work | change requests
project management plan updates
project documents updates
|  | perform integrated change control | approved change requests
change log
project management plan updates
project documents updates
| scope | validate scope | accepted deliverables
change requests
work performance information
project documents updates
|  | control scope | work performance information
change requests
project management plan updates
project documents updates
organisational process assets updates
| schedule | control schedule | work performance information
schedule forecasts
change requests
project management plan updates
project documents updates
organisational process assets updates
| cost | control costs | work performance information
cost forecasts
change requests
project management plan updates
project documents updates
organisational process assets updates
| risk | control risks | work performance information
change requests
project management plan updates
project documents updates
organisational process assets updates
| procurement | control procurements | work performance information
resource calendars
change requests
project management plan updates
organisational process assets updates
| quality | perform quality control | quality control measurements
validated changes
validated deliverables
work performance information
change requests
project management plan updates
project documents updates
organisational process assets updates
| communications | control communications | work performance information
change requests
project documents updates
organisational process assets updates
| stakeholder | comtrol stakeholder engagement | work performance information
change requests
project documents updates
organisational process assets updates
closing | integration | close project/phase | final product, service
result transition
organisational process assets updates
| procurement | close procurements | closed procurements
organisational process assets updates