## Sheet1
REQUIREMENTS TRACEABILITY MATRIX
Project Name: | Hybrid Campus (Phase 1) Project
Project Manager Name: | Yidie Hu, Rui Qin
Project Description: | Hybrid Campus (Phase 1) aims at establishing a studio in Virginia, USA and equipping two study centres in Prato, Italy and Melbourne, Australia respectively. These objectives are expected to be completed within one year.
ID | Requirements (Functional or Non-Functional) | Assumption(s) and/or Customer Need(s) | Category | Source | Status
001 | Study centres should be distributed (Non-Functional) | High demands for OEU's qualifications but little competition with little educational infrastructure |  |  | Not Started
002 | Videoconferencing venue hardware requirement (Functional) | can contain 50 seats, two large television screens, a camera, speakers and a microphone and broadband access to the internet, computer with a document scanner |  |  | Not Started
003 | Studio hardware requirement (Functional) | should be equipped with a camera, computer, presentation and videoconferencing software and two television screens |  |  | Not Started
004 | Lecturers should be able to see live footage of every study centre (Non-Functional) | This can form part of particular lecture |  |  | Not Started
005 | Students should be able to interact with the lecturer (Non-Functional) |  |  |  | Not Started
006 | A student management system (Functional) | A student management system adapted for the particular university, and should be used for all in-semester assessments |  |  | Not Started
007 | student learning management system (Functional) | minimize work for lecturers, without sacrificing quality of assessments |  |  | Not Started
008 | Accreditation from local education authorities (Non-Functional) | campuses and courses offered need to be accredited at local education authorities. |  |  | Not Started
009 | IT and internet infrastructure (Functional) | internet infrastructure differ across countries, the course need a good IT system and strong internet conection |  |  | Not Started
010 | videoconferencing system should be easy to use and training should be provided (Functional) |  |  |  | Not Started
011 | lecturers may also need training (Non-Functional) | student learning management system are difference because it is adapted for the particular university, so lecturers need training |  |  | Not Started
012 | assessment policy and procedures document should be developed (Functional) |  |  |  | Not Started
013 | Exams papers will be scanned and uploaded to a secure folder, processed at head office and marked electronically by lecturers (Functional) |  |  |  | Not Started
014 | Student application, registration and enrolment should be done online (Functional) |  |  |  | Not Started
015 | administrative communication will be done via e-mail (Non-Functional) |  |  |  | Not Started
Note on A5: A unique ID number used to identify the traceability item in the requirements traceability matrix.
Note on B5: This should include a description of the requirement (could be functional or non-functional requirements).
Note on C5: This column should include a description of any assumption or customer need linked to the requirement.
Note on D5: This column specifies whether this requirement is a functional requirement, service requirement, performance requirement, quality requirement or training requirement.
Note on E5: This column specifies the source of the requirement. It could be the source document or person/department initiating it.
Note on F5: This column should include the current status of the requirement.